eMYAA Campaign Briefing for 24F

H2 2026 Upcoming Campaigns Overview

Prepared for the 24F team as part of onboarding, effective from the contract start date of 20 July 2026.

1. Partner Roles for H2 2026

Three specialized partners now split the work that TRACCS previously handled as a single retainer:

24F: organic social content, bilingual copywriting, story management, community monitoring, animated and AI live-action video, monthly reporting. Per the signed Social Media Management Services Agreement (commenced 20 Jul 2026, 6 month minimum, BHD 2,420/mo incl. VAT).

Ignite: paid media buying and ad management across all campaigns. 24F's scope explicitly excludes paid ads, so all sponsored boosts and ad budget management route through Ignite.

Project 2: influencer sourcing and coordination for the 6 confirmed creators on the $5,000 Campaign.

TRACCS is being exited this month with an approximately one month handover overlap. Confirm with Yaqoob/Hatem which in flight TRACCS deliverables (see Section 2) 24F is picking up versus what TRACCS is completing before handover.

2. $5,000 Most Active Trader Raffle

The flagship H2 campaign.

Campaign period: August 1 to December 31, 2026

Draw date: January 10, 2027

Mechanic: every $500 in cumulative trading volume earns one chance to win; prize tier ($500 to $5,000) is set by the winner's own trading volume tier at the time of the draw

Official title: The $5,000 Prize Campaign from eMYAA Platform

Assets already finalized:

Bilingual Terms and Conditions (English and Arabic), currently out for internal approval

Campaign landing pages, English and Arabic, live on the eMYAA website

6 influencer scripts (Ali Sabeel, Musheera, Hamed Al Bloushi, Manal Talal, Abdulelah Alharbi, Ammar Alshaikh), finalized

Support carousel brief: 7 slide Instagram carousel plus 2 filler animation concepts (Entries Update, Final Countdown)

Confirm with TRACCS/24F who executes final design and posting of the support carousel and the launch animation revisions, given the agency transition.

What 24F owns here: organic posting cadence for the carousel and any follow up story content, bilingual copy adaptation if needed, and community monitoring for campaign related comments/DMs (escalate compliance sensitive questions within 2 hours per the agreement).

3. Mention & Win $500 (Recurring Monthly)

Ongoing monthly contest, all 6 GCC countries including UAE

Approved caption lock: "Follow, mention, and open an eMYAA account for a chance to win $500" (English) / Arabic equivalent already approved

Paid boost via Ignite; 24F handles the organic post and story amplification around each monthly cycle

4. Baseline Sponsor Ads

Active August 1 through December 31, 2026 (paused in July)

Instagram and X, weighted toward Instagram, new creative every 2 weeks

Ad spend and boosting managed by Ignite; 24F supplies the underlying creative and copy on the monthly content calendar

5. November App Release

PR support from BFT Media and Dinar

Confirm the specific organic social plan 24F should build around the app release with Hatem/Yaqoob closer to November; not yet finalized as of this briefing.

6. Key Dates at a Glance

| Date | Milestone |
| --- | --- |
| 20 Jul 2026 | 24F contract commences |
| 1 Aug 2026 | $5,000 Campaign and Baseline Sponsor Ads begin |
| 31 Dec 2026 | $5,000 Campaign and Baseline Sponsor Ads end |
| 10 Jan 2027 | $5,000 Campaign draw |
| November 2026 | App release, with BFT Media and Dinar |

7. Points of Contact

24F: Ahmed Bucheery (Creative Director), Munther Mohsen (Senior Project Manager), Abeer Salman (HR and Admin)

Ajyad Capital / eMYAA: Yaqoob Al Balooshi (Head of WealthTech)